## 🚀 Team Iota
Team Iota · Task Flow
Methodology: Scrum ¦ Sprint Length: 2 Weeks ¦ Total Sprints: 4 ¦ Members: 7
📌 PROJECT INFORMATION
Project |  |  | Task Flow – Team Management Service
Objective |  |  | Develop a web-based platform for team collaboration and task management that enables users to create projects, assign tasks, track progress, communicate in real time, and improve workflow efficiency within teams.
👥 TEAM ROSTER
# | Member Name | Role | Sprint Focus | Availability | Status
1 | Rishanth | Scrum Master, Frontend Developer | Sprint Facilitation & UI | 100% | Active
2 | Rohith | Product Owner, UI/UX Designer | Backlog & Design | 100% | Active
3 | Veda | Frontend Developer | UI/UX & Frontend | 100% | Active
4 | Suraj | Backend Developer | API & DB Development | 100% | Active
5 | Abhishek | Testing & Quality Assurance (QA) | Test Automation | 100% | Active
6 | Surya | Deployment & DevOps | CI/CD & Infra | 90% | Active
7 | Akash | Deployment & DevOps | CI/CD & Infra | 90% | Active
📋 SPRINT PLAN — 4 SPRINTS
Start Date: __________ End Date: __________
Sprint | Duration | Goal | Rishanth (Scrum Master & Frontend) | Rohith (Product Owner & UI/UX) | Veda (Frontend) | Suraj (Backend) | Abhishek (Testing) | Surya (DevOps) | Akash (DevOps)
Sprint 1 | 2 Weeks | Requirements Analysis & Authentication | Sprint Planning, Frontend Setup, Team Manage | Requirement Analysis, User Stories, Product Backlog, UI Wireframes | Login UI, Forgot Password UI, API Integration | Database Design, JWT Authentication, Login API, OTP, Google OAuth, User Admin | Authentication Testing, API Testing, Test Cases | Develop Git Repository, Environment Setup | Git Repository, Manage Environment
Sprint 2 | 2 Weeks | User & Team Management | Dashboard UI, Task UI, Team Manage, Sprint Review | UI Review, Feature Stories, Product Backlog Manage | Employee Manage UI, Team Pages | User Manage APIs, Team APIs, Invitation APIs, Transfer APIs | Team Module Testing, Integration Testing | Deployment, Configuration | Docker, h&, Environment Setup
Sprint 3 | 2 Weeks | Task Management & Productivity | Task Dashboard, Sprint Integration | UX Improvements | Task Pages, File Upload UI, Progress UI | Task APIs, Subtask APIs, File Upload, Progress Tracking APIs, Socket.IO | Functional Testing, File Upload Testing | Docker Containerization | Docker Compose Configuration
Sprint 4 | 2 Weeks | Chat, Notifications & Deployment | Chat UI, Notification UI, Sprint Review | Final Product Review | Chat Notification Pages, Polished UI | Chat Socket.IO Backend, Notification APIs, Report APIs, Backend Finalise | System Testing, Regression Testing, Final QA | Render Deployment, Docker Deployment | Jenkins CI/CD Pipeline, Deployment, Automation
🔄 DAILY STAND-UP LOG (Current Sprint)
Date | Team Member | Role | Yesterday | Today | Blockers | Story Pts | Task Status | Help?
Day 1 | Rishanth | Scrum Master | Created project backlog and assigned tasks | Conduct sprint planning meeting | None | 3 | Done | No
Day 1 | Rohith | Product Owner | Finalized requirements and user stories | Review authentication module | None | 2 | Done | No
Day 1 | Veda | Frontend Dev | Designed login page UI | Start implementing login screen | Waiting for backend APIs | 4 | In Progress | Yes – needs help
Day 1 | Suraj | Backend Dev | Designed PostgreSQL schema | Develop JWT authentication and Login API | None | 6 | Done | No
Day 1 | Abhishek | QA Engineer | Prepared authentication test cases | Verify Login API once available | Waiting for backend and frontend | 3 | In Progress | No
Day 2 | Surya | DevOps | Created Git repo and branch strategy | Configure deployment environment | None | 4 | Done | No
Day 2 | Akash | DevOps | Prepared Docker configuration | Test Docker setup locally | Docker version conflict | 4 | Blocked | Yes – needs help
Day 2 | Rishanth | Scrum Master | Reviewed sprint progress | Resolve task dependencies | None | 2 | Done | No
Day 2 | Rohith | Product Owner | Reviewed API requirements | Validate user stories | None | 2 | In Review | No
Day 3 | Veda | Frontend Dev | Completed UI wireframes | Integrate Login UI with APIs | Backend APIs pending | 5 | In Progress | No
Day 3 | Suraj | Backend Dev | Completed Login API and JWT Authenticatio | Implement OTP Verification | None | 8 | Done | No
Day 3 | Abhishek | QA Engineer | Reviewed API test scenarios | Execute authentication API testing | Waiting for completed APIs | 4 | Blocked | Yes – needs help
Day 4 | Surya | DevOps | Configured development environment | Prepare deployment scripts | None | 5 | Done | No
Day 4 | Akash | DevOps | Updated Docker configuratio | Test containerized backend | None | 4 | In Progress | No
Day 4 | Rishanth | Scrum Master | Updated sprint board; removed blockers | Conduct sprint review prep with team | None | 3 | Done | No
📈 SPRINT METRICS & BURN-DOWN SUMMARY
Sprint | Committed | Completed | Remaining | Velocity | % Done | Defects | Fix Rate
Sprint 1 | 42 | 8 | 34 | 8 | 19.05% | 2 | 1
Sprint 2
Sprint 3
Sprint 4