## 🚀 Team Iota
Team Iota · Task Flow
Methodology: Scrum ¦ Sprint Length: 2 Weeks ¦ Total Sprints: 4 ¦ Members: 7
📌 PROJECT INFORMATION
Project |  |  | Task Flow – Team Management Service
Objective |  |  | Develop a web-based platform for team collaboration and task management that enables users to create projects, assign tasks, track progress, communicate in real time, and improve workflow efficiency within teams.
👥 TEAM ROSTER
# | Member Name | Role | Sprint Focus | Availability | Status
1 | Rishanth | Scrum Master, Frontend Developer | Sprint Facilitation & UI | 100% | Active
2 | Rohith | Product Owner, UI/UX Designer | Backlog & Design | 100% | Active
3 | Veda | Frontend Developer | UI/UX & Frontend | 100% | Active
4 | Suraj | Backend Developer | API & DB Development | 100% | Active
5 | Abhishek | Testing & Quality Assurance (QA) | Test Automation | 100% | Active
6 | Surya | Deployment & DevOps | CI/CD & Infra | 90% | Active
7 | Akash | Deployment & DevOps | CI/CD & Infra | 90% | Active
📋 SPRINT PLAN — 4 SPRINTS
Start Date: __________ End Date: __________
Sprint | Duration | Goal | Rishanth (Scrum Master & Frontend) | Rohith (Product Owner & UI/UX) | Veda (Frontend) | Suraj (Backend) | Abhishek (Testing) | Surya (DevOps) | Akash (DevOps)
Sprint 1 | 2 Weeks | Requirements Analysis & Authentication | Sprint Planning, Frontend Setup, Team Manage | Requirement Analysis, User Stories, Product Backlog, UI Wireframes | Login UI, Forgot Password UI, API Integration | Database Design, JWT Authentication, Login API, OTP, User Admin | API Testing, Test Cases | Develop Git Repository, Environment Setup | Git Repository, Manage Environment
Sprint 2 | 2 Weeks | User & Team Management | Dashboard UI, Task Management UI, Sprint Review | UI Review, Feature Stories, Product Backlog Management | Employee Management UI, Team Management UI | User Management APIs, Team Management APIs, Task APIs, Sub-task APIs |  | Environment Variables Configuration | Docker Setup, Environment Setup
Sprint 3 | 2 Weeks | Task Management & Productivity | Sprint Integration & Planning | UX Improvements | Task Pages, File Upload UI, Progress UI | Transfer APIs, File Upload, Progress Tracking APIs, Socket.IO | Functional Testing, File Upload Testing | Docker Containerization | Docker Compose Configuration
Sprint 4 | 2 Weeks | Chat, Notifications & Deployment | Chat UI, Notification UI, Sprint Review | Final Product Review | Chat Notification Pages, Polished UI | Chat Socket.IO Backend, Notification APIs, Report APIs, Backend Finalise | System Testing, Regression Testing, Final QA | Render Deployment, Docker Deployment | Jenkins CI/CD Pipeline, Deployment, Automation
✅ SPRINT 1 DELIVERABLES
Deliverable |  |  | Status
Software Requirement Specification (SRS) |  |  | Completed
Product Backlog |  |  | Completed
Sprint Backlog |  |  | Completed
React Project Initialization |  |  | Completed
Backend Project Initialization |  |  | Completed
Authentication Module (Login, Registration & Admin Dashboard V1) |  |  | Completed
Base CSS Framework |  |  | Completed
Git Repository Setup |  |  | Completed
Sprint Review & PO Approval |  |  | Completed
✅ SPRINT 2 DELIVERABLES
Deliverable |  |  | Status
User Dashboard Implementation |  |  | Completed
Team Management Module |  |  | Completed
Employee Management (CRUD) |  |  | Completed
User Profile Management |  |  | Completed
User & Team Management APIs |  |  | Completed
Task & Sub-task APIs |  |  | Completed
Team & Employee UI Pages |  |  | Completed
Environment Variables Configuration (.env) |  |  | Completed
Docker Environment Setup |  |  | Completed
Sprint Review & Product Backlog Update |  |  | Completed
🔄 DAILY SCRUM LOG (Current Sprint)
Date | Team Member (Role) |  | Task / Activity |  |  | Story Pts | Status | Remarks
26-Jun-26 | Rishanth (SM) |  | Conduct Sprint 2 Planning & Assign Tasks |  |  | 3 | Completed | Sprint initiated
26-Jun-26 | Rohith (PO) |  | Refine Product Backlog |  |  | 3 | Completed | Stories finalized
26-Jun-26 | Entire Team (All) |  | Sprint Kickoff Meeting |  |  | 2 | Completed | Goals discussed
27-Jun-26 | Rishanth (SM) |  | Conduct Daily Scrum |  |  | 2 | Completed | Tasks assigned
27-Jun-26 | Suraj (BE) |  | Design User & Team APIs |  |  | 5 | Completed | Architecture finalized
28-Jun-26 | Holiday |  | No Scrum Activities |  |  | - | - | Weekend
29-Jun-26 | Suraj (BE) |  | Develop User Management APIs |  |  | 8 | Completed | CRUD completed
29-Jun-26 | Surya (DevOps) |  | Configure Environment Variables (.env) |  |  | 3 | Completed | Configuration completed
30-Jun-26 | Rishanth (SM) |  | Sprint Progress Review |  |  | 2 | Completed | Sprint on track
30-Jun-26 | Veda (FE) |  | Develop Dashboard & Team UI |  |  | 5 | Completed | UI progressing
01-Jul-26 | Suraj (BE) |  | Develop Team Management APIs |  |  | 6 | Completed | Endpoints completed
01-Jul-26 | Veda (FE) |  | Develop Employee Management UI |  |  | 5 | Completed | CRUD screens completed
01-Jul-26 | Rohith (PO) |  | Update Product Backlog |  |  | 2 | Completed | Stories updated
02-Jul-26 | Suraj (BE) |  | Develop Task APIs |  |  | 6 | Completed | Task module completed
02-Jul-26 | Veda (FE) |  | Integrate Dashboard & Team UI |  |  | 5 | Completed | Integration successful
03-Jul-26 | Rishanth (SM) |  | Conduct Daily Scrum |  |  | 2 | Completed | No blockers
03-Jul-26 | Suraj (BE) |  | Develop Sub-task APIs |  |  | 5 | Completed | API completed
03-Jul-26 | Akash (DevOps) |  | Validate Docker Environment |  |  | 3 | Completed | Environment stable
04-Jul-26 | Rishanth (SM) |  | Sprint Progress Review |  |  | 2 | Completed | Review completed
04-Jul-26 | Veda (FE) |  | UI Refinements & Bug Fixes |  |  | 3 | Completed | Final UI polish
04-Jul-26 | Rohith (PO) |  | Review Sprint Backlog |  |  | 2 | Completed | Backlog refined
05-Jul-26 | Holiday |  | No Scrum Activities |  |  | - | - | Weekend
06-Jul-26 | Rishanth (SM) |  | Prepare Sprint Review |  |  | 2 | Completed | Review scheduled
06-Jul-26 | Surya (DevOps) |  | Review Environment Configuration |  |  | 2 | Completed | Ready for deployment
07-Jul-26 | Rishanth (SM) |  | Conduct Sprint Review Meeting |  |  | 2 | Completed | Sprint reviewed
07-Jul-26 | Entire Team (All) |  | Feature Demonstration |  |  | 4 | Completed | Features demonstrated
08-Jul-26 | Rishanth (SM) |  | Conduct Sprint Retrospective |  |  | 2 | Completed | Improvements discussed
08-Jul-26 | Rohith (PO) |  | Finalize Product Backlog |  |  | 2 | Completed | Sprint closed
📈 SPRINT METRICS & BURN-DOWN SUMMARY
Sprint | Committed | Completed | Remaining | Velocity | % Done | Defects | Fix Rate
Sprint 1 | 57 | 54 | 3 | 8 | 94.74% | 2 | 1
Sprint 2 | 88 | 88 | 0 | 8 | 100% | 1 | 1
Sprint 3
Sprint 4
PB ID | Feature | User Story | Priority | Story Pts | Sprint | Status
PB-01 | Authentication | Login | High | 8 | Sprint 1 | Completed
PB-02 | Authentication | Register User | High | 5 | Sprint 1 | Completed
PB-03 | Authentication | Reset Password | High | 3 | Sprint 1 | Completed
PB-04 | Dashboard | Admin Dashboard | High | 8 | Sprint 1 | Completed
PB-05 | Dashboard | Develop User Dashboard | High | 10 | Sprint 2 | Completed
PB-06 | Team Management | Implement Team Management Module | High | 10 | Sprint 2 | Completed
PB-07 | Employee Management | Create Employee Management (CRUD) | High | 10 | Sprint 2 | Completed
PB-08 | User Profile | Develop User Profile Management | High | 5 | Sprint 2 | Completed
PB-09 | UI Development | Develop Team & Employee UI | High | 10 | Sprint 2 | Completed
PB-10 | User Management API | Implement User Management APIs | High | 10 | Sprint 2 | Completed
PB-11 | Team Management API | Implement Team Management APIs | High | 8 | Sprint 2 | Completed
PB-12 | Task Management | Develop Task APIs | High | 8 | Sprint 2 | Completed
PB-13 | Task Management | Develop Sub-task APIs | High | 6 | Sprint 2 | Completed
PB-14 | DevOps | Configure Environment Variables (.env) | Medium | 4 | Sprint 2 | Completed
PB-15 | DevOps | Configure Docker Development Environment | Medium | 4 | Sprint 2 | Completed
PB-16 | Team Management | Implement Transfer APIs | Medium | 5 | Sprint 3 | Pending
PB-17 | Backlog Management | Sprint Backlog Review & Refinement | Low | 3 | Sprint 2 | Completed